IMPROVEMENT ADDENDUM TO EXECUTION PLAN v4.0

Agentic AI Logistics Control Tower

What to add on top of v4.0 — ordered by importance

Prepared 24 September 2026 from a read of the dev branch (commit “make the web export reproducible”), the README, benchmarks/, tests/, .github/workflows/ and Execution Plan v4.0. Nothing here replaces v4.0; every item is placed in its calendar. Section 2 rates the project on sixteen aspects out of 10.

# How to read this document

Plan v4.0 is a good plan. It correctly puts the public frontend first, keeps the evidence discipline that is the project's real strength, and already closes several of the biggest earlier gaps (live Kafka, the corrected 30.90-min model, MCP over stdio). This addendum lists only what v4.0 does not cover, plus three places where v4.0 itself needs a correction before work starts.

Items are grouped into three tiers. Tier 1 is small, cheap and fixes things a reviewer or recruiter will notice in the first five minutes — do these first, most of them this week. Tier 2 strengthens the substance of the project and slots into F2 and the paper phase. Tier 3 is polish and scope that only makes sense if Tier 1 and 2 are green.

Rule carried over from v4.0: an item is closed only when a named file, a README change or a logged decision exists. “Fixed in code” without evidence does not close it.

# Scorecard — the project rated on every aspect (out of 10)

Scored against what a strong final-year / master's team project in big-data + agentic AI looks like, not against a production system. A 7 means solid and defensible; a 9 means a reviewer would single it out; a 5 means it exists but would not survive questioning. The last column names the single change that moves the score most — each maps to an item in this addendum.

Overall: 7.8 / 10 today. The engineering underneath is 8–9; what drags it down is what people see first (README, public URL, evaluation size, agentic framing). Closing Tier 1 alone lifts it to about 8.5; Tier 1 + Tier 2 to about 9.

| Aspect | Score | Why this score | What moves it most |
| --- | --- | --- | --- |
| 1. Problem framing & contribution | 8 | Clear two-layer story (audit → predict → act) on real network data; auditing a production routing engine is a genuine, well-scoped contribution. Loses points because the “agentic” headline promises more autonomy than is measured. | B-01 — one measured LLM-decided path, or honest wording |
| 2. Data engineering (Spark pipeline) | 9 | Cleaning with a quality report, trip reconstruction validated against an independent pandas implementation, schema contracts with version bumps (D-016), cached Parquet, 56.4M-row scale appendix. This is the strongest layer. | C-05 lock file; B-08 compose for one-command reproduction |
| 3. Statistical rigour (corridor audit) | 9 | Welch t-tests with FDR correction, a support-floor robustness check that found instability and reported it (D-018), hub dwell analysis. Rare care for a student project. | Nothing urgent; keep it |
| 4. Machine learning | 7 | The v2 GBT (30.90 vs 33.04 median) beats the baseline on all 14 slices and the correction story is honest. Gain is modest (~6.5%), the served model is still v1 (D-053), and the README still shows the old losing number. | A-01 README fix now; C-04 serve v2 later |
| 5. Streaming / real-time | 8 | 886 ev/s produced, 740 ev/s scored, 500/500 stream-equals-batch, Kafka now live and equivalent to the file source. Solid. Not yet exercised in CI, and the stream serves the older model. | A-02 Kafka service container in CI; C-04 |
| 6. Agent layer design | 7 | Five agents + LangGraph orchestrator + MCP server (13 tools, driven over stdio) + versioned prompts + tracing is a complete architecture. But decisions are rule-computed; the LLM only phrases. No approval/governance loop. | B-01 and B-05 approval queue |
| 7. Agent evaluation | 5 | 40/40, 20/20 and 10 lifecycles are far too small; perfect scores on authored cases are not evidence. The 58.6% as-of exception precision is the one honest, believable number. | A-06 — n ≥ 150, adversarial strata, confidence intervals |
| 8. Documentation & evidence trail | 9 | Every result links to a benchmarks/raw/ file, three results freezes, decisions.md, problems.md, weekly writeups per member, release notes. Best-in-class discipline. Only fault: the README itself has drifted from freeze v3. | A-01 |
| 9. Testing & CI | 6 | 26 test files / ~4,300 lines is very good coverage for a student repo — but CI runs only the web export. No test gate on merges; no e2e for the frontend to come. | A-02 pytest in CI; B-04 Playwright |
| 10. Code quality & structure | 7 | Well-organised src/ by plane, clear module names, docstrings that explain decisions. Several 700–1,000-line modules, mixed CRLF/LF, no lint or type checking. | C-01 ruff + mypy, split large modules |
| 11. Reproducibility | 8 | Fresh-clone rebuild recorded (71 min, 35/37 exact), check_env and boot scripts, pinned-floor requirements with reasons written down. Windows-only setup notes and no lock file. | C-03 37/37; C-05 lock file; B-08 compose |
| 12. Security & deployment readiness | 5 | Secrets handled correctly (.env.example, key only on the Space). But v4.0 would publish the TMS write routes, /api/predict has no rate limit, and no monitoring exists. Nothing is public yet. | A-03 TMS isolation; B-03 rate limits; C-02 monitoring |
| 13. Presentation, UX & visibility | 4 | No public URL, no screenshots, no video, no license, no release on main, a 1,004-line Streamlit skeleton. v4.0 exists precisely to fix this, so the score is temporary. | v4.0 F1/F2 as planned + A-04, A-05, B-10 |
| 14. Honesty & scientific integrity | 10 | The Honest Scope section, the reported model correction, the reported replay leak, the “what has never run here” list. This is the project’s defining quality and should be protected. | Keep the README current so the honesty stays accurate (A-01) |
| 15. Team process | 9 | GIT_RULES, weekly gates with tags, PR template, per-member ownership, decision numbering, cost tracking. Professional. | D-069 required CI checks on merge |
| 16. Research / paper readiness | 7 | Claims map, nine figures, paper draft and outline exist; venue chosen. Missing related work, agent ablation, threats-to-validity, model/data cards. | B-09 and B-07 |
| Overall (weighted) | 7.8 | Weights: substance (2–7, 11) 55%; evidence & process (8, 14, 15) 20%; engineering hygiene (9, 10, 12) 15%; visibility (13, 16) 10%. | Tier 1 → ~8.5; Tier 1 + 2 → ~9 |

## Reading the scorecard

- Strongest (9–10): honesty, evidence trail, data engineering, statistical audit, team process. These are what make the project unusual, and none of them needs work beyond keeping the README current.

- Solid (7–8): framing, ML, streaming, agent design, code, reproducibility, paper readiness. Each has one named fix in Tier 2 or 3.

- Weak (4–6): agent evaluation size, CI, security of the planned deployment, and visibility. All four are cheap relative to their effect — they are the whole of Tier 1 plus B-03/B-04 — which is why this addendum orders them first.

- Verdict: yes, a good project — better than most in its category on substance and integrity, and currently under-selling itself. The gap between what exists (≈8.5) and what a visitor can see (≈5) is the thing to close.

# Summary — all items at a glance

| ID | Item | Tier | Effort | Slot in v4.0 calendar | Owner |
| --- | --- | --- | --- | --- | --- |
| A-01 | Fix the stale README (model number, Kafka caveat, pending rows) | 1 | 1 hr | F1 D1 | Lahari |
| A-02 | Run the full pytest suite in CI on every PR | 1 | 2 hr | F1 D1 | Mounika |
| A-03 | Do not expose the mock TMS write routes on the public API | 1 (corrects v4.0 §5.2) | 2 hr | F1 D3 | Mounika |
| A-04 | Confirm main / v1.0 tag; add a LICENSE file | 1 | 30 min | F1 D1 | Sai Krishna |
| A-05 | Cut Gate F1 scope from seven pages to four | 1 (corrects v4.0 §7) | 0 | F1 D1 decision | Sai Krishna |
| A-06 | Enlarge the agent evaluation sets and add confidence intervals | 1 | 1–2 days | F1 D3–D7 (Lahari, parallel) | Lahari |
| B-01 | One genuinely LLM-decided path, measured — or soften the “agentic” wording | 2 | 2 days | F2 D1–D3 | Sai Krishna |
| B-02 | Real (not synthetic) documents in the document-agent evaluation | 2 | 1 day | F2 / cloud week | Sai Krishna |
| B-03 | Rate limiting, input limits and abuse protection on the public API | 2 | half day | F2 D1 | Mounika |
| B-04 | Playwright smoke test of every route in CI | 2 | half day | F1 D6–D7 | Sai Krishna |
| B-05 | Human-approval queue for agent actions (dispute, ticket, order) | 2 | 1–2 days | F2 D1–D3 | Sai Krishna |
| B-06 | Per-run cost and latency in traces, shown on the Agents page | 2 | half day | F2 D1 | Sai Krishna / Mounika |
| B-07 | Model card + data card | 2 | half day | Paper week 1 | Lahari |
| B-08 | docker compose up for the full local stack | 2 | 1 day | F2 D5 / paper week | Mounika |
| B-09 | Paper: agent ablations, related work, threats to validity | 2 | in paper phase | Paper | Lahari |
| B-10 | Two-minute demo video, linked from README and site | 2 | half day | F2 D5 | Sai Krishna |
| C-01 | Code hygiene: ruff + mypy in CI, split 1,000-line modules, normalise CRLF | 3 | 1 day | Paper week / cloud week | all |
| C-02 | Uptime monitor and error tracking for the public URL | 3 | 1 hr | F2 D3 | Mounika |
| C-03 | 37/37 exact on the fresh-clone rebuild (seed the last two) | 3 | half day | Cloud week | Mounika |
| C-04 | Serve the reported v2 model (close D-053) | 3 | 2–3 days | After cloud week | Lahari / Mounika |
| C-05 | Lock file for Python deps; Dependabot | 3 | 1 hr | Any | Mounika |

# Tier 1 — Do first (this week, before or alongside F1)

These are the things that damage credibility today, or that will cost far more if discovered later. None of them takes more than two days; most take an hour.

A-01  Fix the stale README

Effort: 1 hour · Owner: Lahari · Slot: F1 Day 1 · Closes with: README diff + a test that README numbers match results_freeze_v3.json

Why it matters. The README on dev still reports “Random Forest 36.9 min vs OSRM 107.1 min — still 0.8 min behind the corridor-mean baseline”, and its Honest Scope section still says “the Kafka sink has never reached a live broker” and “the MCP server has not been driven by an MCP client over stdio”. Per v4.0 §0 all three are now false: the v2 GBT is at 30.90 min against a 33.04 median baseline, w7_kafka_source_equivalence.json exists, and w7_mcp_stdio_transcript.json exists. The two Results rows marked “pending W7” also have their files. Right now the repository advertises a worse project than the one that exists — and the README is the only thing most visitors will read.

What to do.

- Rewrite the Results table from results_freeze_v3.json: the 30.90 / 33.04 headline, the 14-slice win, the 56.4M-row scale appendix, the MCP transcript, the Kafka equivalence, the assistant route accuracy (0.90).

- Rewrite Honest Scope so that every caveat that has been closed is removed, and every remaining one (G-07 alert channel, D-053 served model, extraction rows 21–40) is stated exactly once.

- Extend tests/test_web_numbers.py (or add tests/test_readme_numbers.py) so that every number in the README results table is parsed and diffed against the freeze. The site is already protected this way; the README should be too.

- Add the model-correction story in one sentence: “A first model (36.9 min) lost to the corridor mean; the corrected v2 GBT (30.90 min) beats the 33.04-min median baseline on all 14 slices (D-048–D-050).” Reporting the correction is a strength.

Done when. README results table and Honest Scope match freeze v3; the README-number test is green in CI.

A-02  Run the full pytest suite in CI on every pull request

Effort: 2 hours · Owner: Mounika · Slot: F1 Day 1 · Closes with: .github/workflows/tests.yml green on dev

Why it matters. There are 26 test files and roughly 4,300 lines of tests, but the only GitHub Action (web.yml) runs the web export and nothing else. A broken commit to src/agents/ or src/tms/ reaches dev with no signal. v4.0 adds test_export_web.py and test_web_numbers.py to CI but still never runs the rest of the suite.

What to do.

- Add tests.yml: Python 3.11 and 3.13 matrix, install requirements, run pytest with the Spark-dependent tests marked and skipped by default (pytest -m "not spark").

- Add a second job that installs JDK 17 (actions/setup-java, temurin) and runs the spark-marked tests. If it is too slow for every PR, run it on push to dev and nightly.

- Add a Kafka service container (bitnami/kafka) to that job so the producer/consumer equivalence test runs in CI rather than only on one laptop. This also closes the last trace of the old “no Docker on the dev machine” caveat permanently.

- Put a status badge for the tests workflow at the top of the README, next to the production URL when it exists.

Done when. tests.yml is required to pass before merging to dev (branch protection rule), and the badge is green.

A-03  Do not expose the mock TMS write routes on the public API — correction to v4.0 §5.2

Effort: 2 hours · Owner: Mounika · Slot: F1 Day 3, when src/api/app.py is scaffolded · Closes with: D-064 logged, OpenAPI spec of the Space shows only /api/* routes

Why it matters. v4.0 §5.2 says the new API “lives in src/api/app.py mounted beside the TMS routes (one uvicorn process)”. The TMS has 14 routes including POST/PUT endpoints that create orders, file tickets and mark invoices disputed. If the same process is published on a Hugging Face Space, anyone on the internet can write into the TMS that the agents and the demo read from. CORS does not protect against this — it only restricts browsers, not curl. The mock TMS is also SQLite on an ephemeral container, so a visitor can corrupt the demo state minutes before a presentation.

What to do.

- Either run two FastAPI apps (public api/app.py; private tms/app.py bound to localhost inside the container) and have the public app call the TMS in-process, or mount the TMS under the same app but require TMS_API_KEY on every TMS route (the .env.example already reserves that variable).

- Make /api/* strictly read-only except /api/predict and /api/ask, both of which write nothing.

- Reset the TMS SQLite file from the seed on container start so any accidental state cannot persist across restarts; document this in docs/deploy_web.md.

- Log the decision as D-064: “The public Space exposes read-only /api/* endpoints only; TMS routes are never reachable without the API key.”

Done when. curl -X POST https://<space>/orders without a key returns 401 or 404, and the runbook says why.

A-04  Confirm main and the v1.0 tag; add a LICENSE file

Effort: 30 minutes · Owner: Sai Krishna · Slot: F1 Day 1 · Closes with: tag visible on GitHub, LICENSE in the root

Why it matters. v4.0 §0 already notes that the clone used for its audit had no tags. The public GitHub page today shows the dev branch as default, and the main branch appears to have no visible commits. A visitor who lands on the repository sees “dev” and no release — the opposite of the “v1.0 complete” message. The README also says “Academic coursework” under License with no LICENSE file, which means the code is technically all-rights-reserved and a recruiter’s company cannot legally run it.

What to do.

- git checkout main && git merge dev; git tag -a v1.0 -m "v1.0"; git push origin main --tags. Create a GitHub Release for v1.0 from docs/RELEASE_v1.0.md.

- Set main as the default branch on GitHub once it is current; the README’s “nobody commits to main” rule is unaffected.

- Add a LICENSE file — MIT or Apache-2.0 for the code — and keep the Delhivery dataset note (Kaggle terms) as a separate DATA_LICENSE.md sentence. Add the Kaggle dataset link and citation.

- Add CITATION.cff so GitHub shows a “Cite this repository” button; it costs five minutes and reads as a research project.

Done when. GitHub shows main as default with a v1.0 release, a license badge, and a Cite button.

A-05  Cut Gate F1 from seven pages to four — correction to v4.0 §7

Effort: none (a decision) · Owner: Sai Krishna · Slot: F1 Day 1 · Closes with: amended Gate F1 text in v4.0, D-057 amended

Why it matters. v4.0 asks one person who may never have shipped React (its own W-09) to deliver Overview, Network, Corridors, Hubs, Evidence, Prompts and About — seven pages including a deck.gl arc map and a virtualised TanStack table — in seven working days, while also learning Next.js, Tailwind and shadcn/ui. The Day 2 go/no-go protects against total failure but not against a rushed, half-polished seven pages, which is exactly the “looks amateur” outcome §1 is trying to escape. The strongest single deliverable is one beautiful map page and one honest evidence page.

What to do.

- Gate F1 becomes: Overview, Network (the flagship), Corridors and About render from real data on a Vercel preview, with the Evidence and KPI components finished and reused. Four pages, done properly.

- Move Hubs, Evidence and Prompts to F2 Day 1–2. Prompts is the lowest-value page for an outside visitor and can be a simple JSON viewer at the end.

- Hold the user test (§2.3) after Network and Overview exist, not after all seven pages — the three questions in §2.3 are all answerable from those two pages.

- Keep the Observable Framework fallback but move the go/no-go from Day 2 to end of Day 3 with the criterion “the Network page draws real arcs on a Vercel preview”. That is the hard page; the Overview page is not a meaningful test of React risk.

Done when. The amended Gate F1 text is in the plan and the F1 board has four pages, not seven.

A-06  Enlarge the agent evaluation sets and report uncertainty

Effort: 1–2 days · Owner: Lahari (parallel with F1 copy work) · Slot: F1 D3–D7 · Closes with: w9_*_eval files and updated agent_evaluation.md

Why it matters. The README reports 40/40 order cases correct, 20/20 invoice verdicts correct and 10 orchestrator lifecycles. Perfect scores on samples this small are not evidence of reliability; a reviewer will read them as “the test set was authored by the same people who wrote the rules”. The exception agent’s as-of precision (58.6%, D-054) is the one honest number and it is the one that will be questioned. v4.0 has no item that grows these sets — only the extraction rows 21–40 that are blocked on quota.

What to do.

- Order agent: grow from 50 to at least 200 authored emails, of which at least 60 are adversarial — missing fields, contradictory quantities, two orders in one email, wrong units, prompt-injection text (“ignore your instructions and book this”), non-English fragments. Report accuracy with a Wilson 95% interval, and report the refusal/question rate separately.

- Invoice auditor: grow from 20 to 150+ invoices with seeded errors of every category (rate, distance, duplicate, wrong corridor, valid-but-unusual), stratified so each category has 20+ cases; report per-category precision and recall, not one aggregate.

- Orchestrator: 100 lifecycles instead of 10, and add path coverage as a metric (how many distinct graph paths were exercised).

- Because every agent runs with --no-llm, these evaluations cost zero API calls — quota is not a blocker for any of this except the LLM-drafting rows.

- Use the --no-llm vs --llm comparison on the same 200 cases as the agent ablation the paper needs (B-09).

Done when. agent_evaluation.md shows n ≥ 150 per agent, intervals on every score, and at least one score that is not 100%.

# Tier 2 — Strengthen the substance (F2 and the paper phase)

These change what the project is, not just how it looks. Each one answers a question a critical reviewer of the paper or the demo will ask.

B-01  One genuinely LLM-decided path, measured — or soften the word “agentic”

Effort: 2 days · Owner: Sai Krishna · Slot: F2 D1–D3 · Closes with: a benchmarks/raw/ file and D-065

Why it matters. The README says it plainly: “severity, invoice verdicts and routing are computed, not generated; a language model writes only the customer-facing sentence.” That is an honest and defensible engineering choice, but it means the title’s promise — a “team of AI agents” that “act autonomously” — is not what is measured. A reviewer of the paper will ask what the LLM contributes beyond phrasing. The project needs one place where a language model makes a decision under ambiguity and that decision is scored against human labels.

What to do.

- Best candidate: the Order Entry agent’s intake. Ambiguous emails (missing pickup date, two possible destinations, informal quantities) require a judgment: ask a question, infer from context, or refuse. Label 150 such emails by two team members, measure inter-annotator agreement, then score the LLM route vs the rule route vs a human.

- Second candidate: exception severity when the model’s delay prediction and the corridor’s historical band disagree — let the LLM reason with both and a short policy, and measure against operator-style labels.

- Report the results as a three-way comparison (rules / LLM / human) and put the honest result on the Agents page and in the paper. If the LLM loses, that is still a publishable finding.

- If this cannot be done in the calendar, change the title language on the site and in the paper from “autonomous agents” to “LLM-assisted automation agents with reproducible decisions” and keep the current design. Either path is fine; the current mismatch is not.

Done when. One agent has a measured LLM-decision component with a human-labelled test set, or the wording is changed and logged.

B-02  Real documents in the document-agent evaluation

Effort: 1 day · Owner: Sai Krishna · Slot: F2, or the cloud week alongside the Textract benchmark · Closes with: w*_doc_eval_real.json

Why it matters. The Document Intelligence agent is scored on a 300–500 document synthetic corpus the team generated. 97.9% field accuracy on documents produced by your own generator measures the generator as much as the extractor. The cloud week’s 150-document Textract benchmark appears to use the same corpus.

What to do.

- Assemble 30–50 real, messy scanned invoices, receipts and bills of lading from public sources (e.g., the SROIE receipt dataset, FUNSD forms, CORD receipts, and any freely licensed logistics documents), plus 10 photographed on a phone by the team with skew, shadows and creases.

- Score the agent on this out-of-distribution set with the same field-level metric and report both numbers side by side: synthetic 97.9% vs real X%. The gap is the finding.

- Run the same real set through Textract in the cloud week so the OCR comparison is on documents the team did not manufacture.

Done when. The Evidence page and the paper show synthetic and real accuracy side by side.

B-03  Rate limiting, input limits and abuse protection on the public API

Effort: half a day · Owner: Mounika · Slot: F2 D1 with the Space publish · Closes with: docs/deploy_web.md section and a test

Why it matters. v4.0 caps /api/ask at 10 LLM calls per day but leaves /api/predict unprotected. A predict call spins Spark; a loop of a few hundred requests from one script will keep the free Space pegged and make the demo feel broken. The public site’s IP will be posted on CVs, so it will be scanned.

What to do.

- Add slowapi (or a simple in-memory token bucket) per client IP: e.g., 30 /api/predict calls per minute, 5 /api/ask per minute, and a global concurrency limit of 2 on predict so Spark is never asked to score more than two batches at once.

- Validate every input with Pydantic bounds: planned time and distance within the ranges seen in the data; corridor id must exist; request body size limited by uvicorn --limit-max-requests / a body-size middleware.

- Return structured 429 responses that the UI turns into a “busy — try again in a moment” state, matching the “warming” state pattern in §5.3.

- Log every request with latency and status (structured JSON) so the f1_api_latency.json measurement can be re-run from production logs.

Done when. A load test of 200 requests from one IP shows 429s, no 5xx, and the Space stays responsive for a second client.

B-04  Playwright smoke test of every route in CI

Effort: half a day · Owner: Sai Krishna · Slot: F1 D6–D7 (with the Lighthouse run) · Closes with: web/e2e/ and a CI job

Why it matters. v4.0 protects the numbers (test_web_numbers.py) and the performance (Lighthouse) but nothing checks that each page actually renders without a console error after a change. The static export will happily succeed with a page that throws on hydration.

What to do.

- Add Playwright with one test per route: navigate, assert the page headline is present, assert no console errors, take a screenshot. For /network assert that the canvas exists and at least one arc was drawn (deck.gl exposes layer state).

- Run against the built static export in CI on every PR (pnpm build && npx serve out &). Attach the screenshots as CI artefacts so a reviewer can see every page from the PR.

- Reuse the screenshots for the README and docs/figures/web/ so they stay current automatically (W-08).

Done when. The e2e job is required for merge, and the PR page shows ten screenshots.

B-05  Human-approval queue for agent actions

Effort: 1–2 days · Owner: Sai Krishna · Slot: F2 D1–D3 (Agents page) · Closes with: a route on the site and a decision log entry

Why it matters. The agents file tickets, dispute invoices and book orders with no human in the loop — Gate 6 celebrates this. In real logistics operations that is not a feature: nobody lets an automated auditor dispute a carrier invoice without a person clicking approve. The current best practice for agent systems (and the thing every industry talk in 2026 asks about) is a governed loop: the agent proposes, a human approves above a risk threshold, and the system records who approved what.

What to do.

- Add an approval state to the TMS: actions above a threshold (dispute amount over X, severity “critical”, orders with any inferred field) land in a pending queue instead of executing.

- Add an /approvals page (or a drawer on /agents) listing pending actions with the agent’s reasoning and evidence; approve/reject writes back through the API with a reviewer id. In the public deployment this is read-only with a recorded queue, exactly like the alerts fallback.

- Measure and report the auto-approval rate: what fraction of actions were low-risk enough to execute unattended. That number is a better story than “no human in the loop”.

Done when. The lifecycle graph shows an approval node, and agent_evaluation.md reports the auto-approval rate.

B-06  Per-run cost and latency in traces, shown on the Agents page

Effort: half a day · Owner: Sai Krishna (tracing) / Mounika (export) · Slot: F2 D1 · Closes with: fields in the trace log and agents.json

Why it matters. docs/cost.md tracks total spend, but no trace records how long an agent run took, how many tool calls it made, or how many tokens the LLM draft consumed. The Agents page in v4.0 shows role, score and last action; adding “median 1.8 s, 3.2 tool calls, 410 tokens, $0.0002 per run” is what makes it read as an engineered system rather than a script.

What to do.

- Extend src/agents/tracing to record wall time, tool-call count, LLM token counts (from the provider response) and a computed cost per run.

- Export aggregates per agent into agents.json; show them on the agent cards and in the trace drawer.

- Add one chart on /evidence: cost per lifecycle with and without --llm.

Done when. Each agent card on the public site shows latency, tool calls and cost.

B-07  Model card and data card

Effort: half a day · Owner: Lahari · Slot: paper week 1 · Closes with: docs/model_card.md and docs/data_card.md, linked from /about

Why it matters. The project has an unusually complete evidence trail but it is spread across decisions.md, results.md and benchmarks/. A one-page model card (intended use, training data window, features, metrics by slice, known failure modes — cold-start corridors, the D-053 serving gap, the replay leak) and a data card (Delhivery source, 144,867 segments, cleaning drops from _quality_report.json, what a “leg” is) are the standard artefacts a reviewer expects and a recruiter recognises.

What to do.

- Follow the Hugging Face model-card and datasheets-for-datasets templates; fill only from existing files so every number traces.

- Publish the model card on the Hugging Face Space README as well, so the Space page is not empty.

Done when. Both cards exist, are linked from /about and the paper’s appendix, and pass test_web_numbers.py.

B-08  docker compose up for the full local stack

Effort: 1 day · Owner: Mounika · Slot: F2 D5 or paper week · Closes with: docker-compose.yml and a README section

Why it matters. The README quickstart is eight numbered steps with Windows-specific JDK and Tesseract workarounds. w8_fresh_clone_rebuild.json shows 71 minutes for a rebuild. A single docker compose up that starts Kafka, the TMS, the API and the web dev server — with the data caches mounted — turns “reproducible in principle” into “reproducible in one command”, and gives macOS/Linux users a path the README currently does not.

What to do.

- Services: kafka, tms, api (JDK 17 + PySpark, reusing deploy/api_space/Dockerfile), web (node), plus a one-shot pipeline service that builds the caches from data/raw if they are missing.

- Add macOS/Linux equivalents of the Windows setup commands to the README, or point them at compose.

- Run the compose build in the nightly CI job so it cannot rot.

Done when. A fresh machine with Docker reaches the dashboard with the three commands: clone, place the CSV, docker compose up.

B-09  Paper: agent ablations, related work, threats to validity

Effort: within the paper phase · Owner: Lahari (with Sai Krishna for the agent section) · Slot: 12–23 Oct · Closes with: sections in paper_draft.md

Why it matters. v4.0 §11.1 covers the claims map and what not to claim, but three sections reviewers look for first are not in the outline: an ablation of the agent layer (rules only vs rules+LLM vs LLM-decided, from A-06/B-01), a related-work section positioning the work against existing control-tower and agentic-supply-chain systems (at least the academic ones on OSRM auditing, delay prediction on the Delhivery dataset — there are several Kaggle and paper baselines — and LLM agents for operations), and a threats-to-validity section that owns the synthetic scaffolding, the single-carrier dataset, the replay leak and the small evaluation sets.

What to do.

- Write the related-work paragraph early — it may change what the headline claim should be. Search specifically for prior delay-prediction results on the same Delhivery Kaggle dataset and report them as a comparison row.

- Add the ablation table from A-06 and B-01.

- Add a threats-to-validity section using the Honest Scope text as the seed; it is already most of the way there.

Done when. paper_draft.md has all three sections and the claims map references the ablation table.

B-10  Two-minute demo video

Effort: half a day · Owner: Sai Krishna · Slot: F2 D5 (v4.0 already plans a 30-second recording) · Closes with: a YouTube/Loom link at the top of the README and on /about

Why it matters. v4.0 plans a 30-second screen recording. Thirty seconds shows that the site exists; two minutes with narration shows what it does — audit → predict → act — and is the artefact most people will actually consume from a CV or a LinkedIn post. It also survives the free tiers sleeping.

What to do.

- Script from docs/demo_script.md: 20 s problem, 40 s network map and a bottleneck story, 30 s live prediction and alert, 30 s an agent lifecycle and the invoice verdict, 10 s honest scope.

- Record on the production URL after the user test, with captions; keep the 30-second cut as the README GIF.

Done when. The video link is the second line of the README, under the production URL.

# Tier 3 — Polish and later scope

Worth doing, but only after the tiers above are green. Each is short.

C-01  Code hygiene: ruff + mypy in CI, split the 1,000-line modules, normalise line endings

Effort: 1 day spread across the team · Slot: paper week / cloud week

Why it matters. src/ml/audit.py (1,078 lines), src/dashboard/app.py (1,004 — going away), src/report/export_web.py (796), src/ml/models.py (706) and src/tms/app.py (664) are large single files; several source files carry Windows CRLF endings alongside LF files. None of this is wrong, but a reviewer opening the code will notice it before noticing the tests.

What to do.

- Add ruff (lint + format) and mypy --strict on src/common and src/agents to CI; fix what they find incrementally.

- Split audit.py into stats / reporting / cli; split export_web.py per JSON contract (it already has one function per file in Appendix B).

- Add .gitattributes with * text=auto eol=lf and renormalise once; add pre-commit with ruff, nbstripout and the secret scan D-062 already calls for.

Done when. ruff and mypy jobs are green; no file over 600 lines in src/.

C-02  Uptime monitor and error tracking for the public URL

Effort: 1 hour · Owner: Mounika · Slot: F2 D3

Why it matters. v4.0 has a keep-warm cron but nothing that tells the team when the site or the Space is down. The first person to find out will be someone clicking the link from a CV.

What to do.

- UptimeRobot (free) on the Vercel URL and /health on the Space, alerting to the team’s Telegram — which also gives the alert bot’s Telegram channel a real credential, helping G-07.

- Sentry’s free tier on the frontend for uncaught errors; the API already logs.

Done when. A deliberate outage of the Space produces a Telegram message within five minutes.

C-03  37 of 37 exact on the fresh-clone rebuild

Effort: half a day · Owner: Mounika · Slot: cloud week

Why it matters. w8_fresh_clone_rebuild.json reports 35 of 37 numbers reproduced exactly. Find the two that drift (almost always an unseeded random split or a Spark partition-order dependency), pin them, and re-run. “Bit-for-bit reproducible” is a stronger sentence in the paper than “35 of 37”.

What to do.

- Diff the two values, locate the nondeterminism, set seeds / sort before aggregation, re-run, update the file.

Done when. The rebuild file says 37/37 and the paper says so.

C-04  Serve the reported v2 model (close D-053)

Effort: 2–3 days · Owner: Lahari / Mounika · Slot: after the cloud week

Why it matters. The stream and the public predictor serve the Week 4 champion, not the 30.90-min v2 GBT, because v2 needs event-time state. v4.0 handles this honestly with model_id in every response. Closing the gap is the natural next engineering milestone once the web is live: the paper’s headline model should be the one the demo scores with.

What to do.

- Implement the stateful feature (event-time corridor running stats) in Structured Streaming with a watermark; validate stream-equals-batch again for v2 as was done for v1 (500/500).

Done when. model_id on the predictor result reads v2, and a new stream-equals-batch file exists for it.

C-05  Lock file for Python dependencies; Dependabot

Effort: 1 hour · Owner: Mounika · Slot: any

Why it matters. requirements.txt uses floors (>=), which is right for a library and wrong for a reproducible research artefact: a fresh install in six months will resolve different versions. The 71-minute rebuild should install the exact versions that produced freeze v3.

What to do.

- pip-compile requirements.txt into requirements.lock (or use uv lock); CI and the Dockerfiles install from the lock; enable Dependabot for security updates only.

Done when. The lock file is committed and both Dockerfiles use it.

# Where each item lands in the v4.0 calendar

| Phase (v4.0 §6) | Add from this addendum | Cost to the phase |
| --- | --- | --- |
| F1 D1 (Wed 24 Sep) | A-01 README fix · A-02 tests in CI · A-04 main/tag/LICENSE · A-05 scope decision | About half a day across three people; no frontend time lost |
| F1 D3–D7 | A-03 TMS isolation (when api/app.py is scaffolded) · A-06 evaluation growth (Lahari, parallel) · B-04 Playwright (with the Lighthouse run) | Lahari’s copy work shrinks slightly because A-05 reduces pages to write copy for |
| F2 D1–D3 | B-03 API protection · B-05 approval queue · B-06 cost/latency in traces · B-01 LLM-decided path | B-05 and B-01 are the two real additions; Hubs/Prompts/Evidence pages moved here from F1 balance it |
| F2 D3–D5 | C-02 uptime monitor · B-10 two-minute video (replaces the 30-second one) · B-08 compose (if time) | Small |
| Paper (12–23 Oct) | B-07 model/data cards · B-09 ablations, related work, threats · C-01 hygiene in the gaps | Inside the existing writing load; B-09 depends on A-06 and B-01 having run |
| Cloud week (26–30 Oct) | B-02 real documents through Textract · C-03 37/37 · C-05 lock file | Fits the existing Textract benchmark |
| After | C-04 serve v2 | Next milestone, v1.3 |

# Decision-log entries to add

Continue from D-063 in v4.0 §12.

| ID | Decision |
| --- | --- |
| D-064 | The public API Space exposes read-only /api/* routes plus /api/predict and /api/ask; TMS routes are never reachable without TMS_API_KEY, and the TMS database is re-seeded on every container start. |
| D-065 | Either: one agent (Order Entry intake) has a measured LLM-decision component scored against a two-annotator human label set; or: public wording changes from “autonomous agents” to “LLM-assisted automation agents with reproducible decisions”. Record which. |
| D-066 | Gate F1 is four pages (Overview, Network, Corridors, About); Hubs, Evidence and Prompts move to F2 D1–D2. The Observable fallback go/no-go is end of F1 D3 on the Network page. |
| D-067 | Agent actions above a risk threshold require human approval; the auto-approval rate is a reported metric. |
| D-068 | Every agent evaluation reports n ≥ 150 with a Wilson 95% interval; adversarial cases are a stratum of every set. |
| D-069 | The full pytest suite, ruff and the Playwright e2e job are required checks for merging to dev. |

# What not to add

Because the calendar is already full, it is worth naming things that were considered and rejected for this phase:

- Rewriting MLlib to scikit-learn — v4.0 §5.3 is right; the Spark claim is the paper.

- A user login or multi-tenant TMS — the demo is single-operator by design.

- A mobile app or a Slack bot — the alert bot already has channels; configuring one (G-07) is enough.

- More agents. Five plus an orchestrator is the right number; deeper evaluation of the five beats a sixth.

- Kubernetes or any of the never-create AWS list — the $0 hosting story is part of the project’s credibility.