EXECUTION PLAN — VERSION 3.1

Agentic AI Logistics Control Tower

11-week plan · Weeks 7–8 completion · ML correction sprint · Paper · One-week cloud phase on a $40 credit

Team: Sai Krishna (AI Agents & Automation) · Lahari (ML & Evaluation) · Mounika (Data & Systems)

Prepared 16 September 2026 · v3.1 compresses the cloud phase to one week and fits a $40 credit · Supersedes v2.0 from Week 7 onward · Weeks 1–6 stand as executed · Calendar mapping below assumes Week 7 begins Monday 21 September; shift every date if it begins earlier.

Why this version exists. The repository is at the end of Week 6 with 178 commits on dev and every Week 1–6 deliverable built. Three things changed since v2.0 was written: an audit of the repo against the v2 gates found eleven open gaps (one of them a Week 4 gate half that was never reported); the Week 4 model result needs a correction sprint before it enters the paper; and a post-v1.0 cloud phase has been added so the work becomes reachable by anyone with a browser. This document carries all three, plus the Week 7–8 plan from v2.0 with the gaps folded in.

# 0. Status Audit — Where the Repository Actually Stands

Read from the benchmarks/raw/ files and the README results table on 16 September 2026. A week counts as done only when its benchmark evidence exists, not when its code exists.

| Week | Gate (v2.0) | Evidence in the repo | Status |
| --- | --- | --- | --- |
| 1 | Cleaned Parquet v1; every member loads it in Spark; LLM API responds | clean_v1, check_env, _quality_report.json | Done |
| 2 | Bottleneck corridor audit + India map | 4 result rows (audit, support-30 robustness, hub dwell, map) | Done — marked met, tagged |
| 3 | Feature table frozen; baselines on the board; 100+ labelled synthetic documents | No W3 result row. Features and corpus clearly exist (W4 models trained; auditor ran on seeded ground truth) | Done — not recorded (G-10) |
| 4 | Batch ML complete with beat-OSRM headline; Doc Agent extracting with measured accuracy | w4_model_metrics.csv exists. No document-extraction accuracy file exists | Half done (G-01) · headline weak (G-04) |
| 5 | Replayed event → live dashboard alert; Order Entry Agent posting to TMS | 4 result rows (throughput, stream=batch, threshold sensitivity, order eval 40/50) | Done — marked met · 10 cases open (G-02) |
| 6 | Full lifecycle agent-to-agent with no human in the loop | w6_orchestrator_runs.json, w6_invoice_audit_runs.json | Done — not marked met (G-03) |
| 7 | RAG assistant; agent-eval report; scale appendix | Both README rows say pending W7 | Not started |
| 8 | Demo rehearsed twice; paper outline + figures; v1.0 | — | Not started |

Position: end of Week 6 of 8, on schedule. Nothing is broken. What follows is a gap register, then the plan that closes every gap while finishing Weeks 7 and 8 as written.

## 0.1 Open Gaps Register

Every gap closes with a benchmark file or a README change. "Fixed in code" without evidence does not close a gap. Each G-number is referenced from the week tables below so nothing is closed by accident or forgotten.

| ID | Gap | Why it matters | Owner | Closes in |
| --- | --- | --- | --- | --- |
| G-01 | Document-extraction accuracy never measured or reported | Half of the Week 4 gate. Agent ① is the only one of five agents with no score — the results table is visibly incomplete | Sai Krishna builds · Lahari judges | W7 D1–D2 |
| G-02 | Order Entry evaluation stopped at 40 of 50 cases (quota) | A published "40/40" invites "why not 50?" | Lahari | W7 D4 |
| G-03 | Gates 3, 4, 6 not marked met; tags week3/4/6-complete missing; main behind dev | README makes the team look two weeks behind reality | Mounika | W7 D5 |
| G-04 | Random Forest 36.9 min MAE is behind the corridor-mean baseline (36.1); probable MLlib categorical-feature bug; squared-loss training graded on MAE | The paper's ML headline is currently a negative result dressed as a 65% win over OSRM, which reviewers will attack | Lahari + Mounika | W7 D1–D3 (sprint) |
| G-05 | Kafka sink has never reached a live broker (D-035) | Most-cited caveat in Honest scope; undermines the streaming claim | Mounika | W7 D3 |
| G-06 | MCP server never driven by an MCP client over stdio | "MCP server" is on the architecture diagram and the resume line | Sai Krishna | W7 D4 |
| G-07 | Alert bot Telegram/email channels implemented but unconfigured (D-039) | Only the file channel has ever sent anything | Sai Krishna | W7 D5 |
| G-08 | No public URL — dashboard needs JDK 17 + Kaggle download + Spark before anyone sees it | Nobody outside the team will ever see the work | Sai Krishna | W8 D3 |
| G-09 | Paper headline framed as "beats the production planner" | OSRM is a planner, not a predictor; the comparison is structurally unfair and the model trails a mean | Lahari | W8 D3–D4 |
| G-10 | No Week 3 result row in the README | Bookkeeping; feeds G-03 | Mounika | W7 D5 |
| G-11 | No calendar/festival feature although the data window (autumn 2018) likely spans Navratri–Dussehra — verify the actual date range first | A free, India-specific signal no other Delhivery-dataset project has; drop it if the window is too narrow | Mounika | W7 D1 (conditional) |

## 0.2 Gap Closure Checklist — the artefact that proves each gap is closed

Tick a row only when the named file or change is merged to dev. This is the Gate 7 / Gate 8 walk-through.

| ID | Closing artefact | Where | When |
| --- | --- | --- | --- |
| G-01 | benchmarks/raw/w7_doc_extraction_eval.json + _summary.csv; README results row; document row in agent_evaluation.md | §2 Sai Krishna D1–D2 | W7 D2 |
| G-02 | w5_order_eval_summary.json shows 50 cases (or the real number with the reason) | §2 Lahari D4 | W7 D4 |
| G-03 | Gate table shows 3/4/6 met; tags exist on main; main == dev at week7-complete | §2 Mounika D5 | W7 D5 |
| G-04 | w7_model_metrics_v2.csv with slices; D-044 and D-045 in decisions.md; paper framing per outcome | §2.1 | W7 D3 |
| G-05 | w7_kafka_live.json; D-035 caveat removed from Honest scope | §2 Mounika D3 | W7 D3 |
| G-06 | w7_mcp_stdio_transcript.json; caveat removed | §2 Sai Krishna D4 | W7 D4 |
| G-07 | w7_alert_channel_live.json; D-039 caveat removed | §2 Sai Krishna D5 | W7 D5 |
| G-08 | Public URL at the top of the README (Streamlit Community Cloud, $0) | §3 Sai Krishna D3–D4 | W8 D4 |
| G-09 | Paper outline headed by the corridor audit; D-049 logged | §3 Lahari D3–D4 | W8 D4 |
| G-10 | Week 3 row in the README results table | §2 Mounika D5 | W7 D5 |
| G-11 | Either is_festival_window in features_v2 or a one-line note in D-044 that the date range does not cover it | §2 Mounika D1 | W7 D1 |

What the plan can and cannot promise on G-04. The sprint is guaranteed to produce a defensible, honest ML section — the three-outcome rule in §2.1 Step 5 covers every result. It is not guaranteed to beat 36.1 minutes; that depends on the diagnostics. If the categorical-as-numeric bug is present, expect a clear win. If the features simply carry no signal beyond corridor history, the paper leads with the audit and the ML section reports a tie honestly — which is still a complete, publishable result.

# 1. Operating Rhythm

Unchanged from v2.0 — 5 working days, D1–D5; 30-minute weekly sync with decisions logged in docs/decisions.md; one branch per member per week off dev; weekend PR reviewed by a teammate; gates merge dev → main with a tag; branches kept after merge. Four additions:

- Controlled unfreeze. The Layer 1 results freeze (v2.0, W6 D1–D2) is reopened for exactly three days, W7 D1–D3, for one purpose: the ML correction sprint in §2.1. Results v1 are archived untouched as benchmarks/raw/w4_model_metrics.csv; the sprint writes w7_model_metrics_v2.csv. Whichever the team adopts becomes the paper's number and the other becomes an ablation row. Log this as D-044 on W7 D1 before any code changes.

- Evidence closes gaps. A G-number closes only when its benchmark file or README change is merged to dev. The W7 and W8 gate checks walk the register.

- Cloud is optional, always. From Phase 3 onward, python -m src.common.boot must run to completion with zero AWS configured. Cloud is a backend selected by .env, exactly as --no-llm selects template wording today. Any change that breaks the local path is reverted.

- Commit convention: as GIT_RULES.md §7 — short lowercase imperative, no bracketed prefix. The v2.0 text that said [W3][AGENT] ... was wrong and has already been corrected in the README.

## 1.1 Calendar

| Phase | Weeks | Dates (shift if W7 starts earlier) |
| --- | --- | --- |
| Completion | W7 – W8 | Mon 21 Sep – Fri 2 Oct 2026 · v1.0 tagged Fri 2 Oct |
| Paper | W9 – W10 | Mon 5 Oct – Fri 16 Oct · full draft + arXiv preprint |
| Cloud deployment | W11 only | Mon 19 Oct – Fri 23 Oct · v1.1-cloud tagged Fri 23 Oct · total AWS spend capped at $40 |

# 2. Week 7 — Close the Gaps, Correct the Model, Finish the Intelligence Layer

Gate 7: assistant answers grounded questions live · document-extraction accuracy recorded (G-01) · consolidated agent-evaluation table covers all five agents · ML v2 decision logged (G-04) · Kafka live-broker numbers recorded (G-05) · scale appendix table produced · gates 3/4/6 back-tagged and README results table complete (G-03, G-10). Merge → main, tag week7-complete.

| Member | D1–D2 | D3–D4 | D5 |
| --- | --- | --- | --- |
| Sai Krishna | G-01. Save eval_extraction.py as src/ml/eval_extraction.py. Wire run_extraction() to the Document Intelligence Agent and load_corpus() to the real corpus layout. Run on 5 docs, then full corpus. Commit benchmarks/raw/w7_doc_extraction_eval.json + _summary.csv. Fix the weakest 3 fields the script prints — one prompt iteration only, re-run, commit both runs. | Analytics Assistant (RAG over the vector DB) embedded in the dashboard; refusal fallback for out-of-scope questions. G-06. Drive src.agents.mcp_server from a real MCP client over stdio (MCP Inspector or a 20-line Python client); capture the tool-call transcript to benchmarks/raw/w7_mcp_stdio_transcript.json. Agent tracing page: every agent call logged with inputs/outputs. | Prompt library finalised and versioned; assistant run on the fixed 30-question set. G-07. Configure one real channel (SMTP email is simplest; Telegram if a bot token is easy). Send one real alert from the replay; record in w7_alert_channel_live.json. |
| Lahari | G-04 sprint, D1. Run the four diagnostics in §2.1 Step 1 and write the findings to docs/decisions.md D-044 before changing any model code. D2. Residual target + GBT absolute loss on feature table v2 (§2.1 Step 3). Train RF and GBT on residual; assemble prediction = baseline + residual. | D3. Slice-wise evaluation (§2.1 Step 4) → w7_model_metrics_v2.csv. Adopt/keep decision at the D3 sync, logged as D-045 with the decision rule in §2.1 Step 5. D4 · G-02. Run the last 10 Order Entry cases → update w5_order_eval_summary.json to 50/50 (or report the real number). Consolidated agent-evaluation table — five agents, one table — benchmarks/agent_evaluation.md. | Groundedness judging of the 30-question set with Sai Krishna; experiments appendix: every reported number points to a script and a cache. |
| Mounika | G-04 sprint / G-11, D1. Verify the dataset's actual date range; if it spans Navratri–Dussehra, add is_festival_window. Build feature table v2 (§2.1 Step 2): hub dwell by departure hour (origin + destination), corridor std/p90/IQR, trailing 7-day and 30-day corridor mean, historical actual/OSRM ratio, segment count. D2. Cache features_v2 Parquet; bump the contract version (D-016 rule — never repoint v1); python -m src.pipeline.contracts --keys green. | G-05, D3. Bring Kafka up on any machine with Docker — GitHub Codespaces (free allowance, Docker present) is the zero-cost route. Producer → live broker → streaming.job → sink. Capture sustained events/sec and event-to-alert p50 → w7_kafka_live.json. Then delete the D-035 caveat from Honest scope. D4. Scale appendix: identical corridor-aggregation Spark code on 50M+ NYC taxi rows (local Spark; a multi-core run is the scale evidence for this plan); runtime table rows × cores × time → benchmarks/scale_appendix.md. | G-03 / G-10. Add the Week 3 result row (feature table row count, corpus size, baseline MAEs). Mark gates 3, 4, 6 met; create tags week3-complete, week4-complete/batch-complete, week6-complete on the right dev commits; merge dev → main. Streaming stress numbers finalised. |

## 2.1 The ML Correction Sprint (W7 D1–D3), Step by Step

The problem in one sentence: a Random Forest that should never lose to a per-corridor average is losing to it by 0.8 minutes. That points to a defect, not a limit. The sprint diagnoses first and changes the target second.

### Step 1 — Diagnose before touching hyperparameters (Lahari, D1)

- Categorical-as-numeric check. Open the feature assembly code. If the corridor key goes StringIndexer → VectorAssembler with no VectorIndexer or categorical metadata in between, MLlib is treating the index as a quantity and splitting on alphabetical order. Also check maxBins: it must be ≥ the number of categories (1,130+); the default is 32. Either finding alone explains the symptom.

- Is the corridor statistic actually in the vector? Print the assembled feature names. If the past-only corridor mean is not among them, the model is rediscovering from scratch what the baseline gets for free.

- Corridor-median baseline. If MAE is the reported metric, the fair baseline is the per-corridor median, not mean — the median minimises absolute error by construction. Three lines of code. It may be stronger than 36.1; better to know now than after submission.

- Single-node reference ceiling. 26,369 legs fits in memory trivially. Train LightGBM or sklearn HistGradientBoostingRegressor on the same features in seconds. If it also cannot beat the baseline, the problem is features; if it beats it comfortably while MLlib does not, the problem is MLlib configuration (Step 1a). MLlib remains the reported model — this is a diagnostic only.

### Step 2 — Feature table v2 (Mounika, D1–D2)

The Week 2 result that points at the missing signal: median leg dwell is 49 minutes — 34.6% of wall clock. A third of the target variable is spent parked at hubs, and a corridor mean averages straight over it. Add, in this order of expected value:

| Feature | Why |
| --- | --- |
| Origin-hub and destination-hub historical dwell, by departure hour | Dwell is a queueing phenomenon; it varies by time of day far more than by corridor. Already computed at hub level in W2 — this is a join plus an hour bucket. |
| Corridor dispersion: std, p90, IQR (past-only) | High-variance corridors deserve different predictions from stable ones; the mean hides this. |
| Trailing 7-day and 30-day corridor mean | Captures drift the all-time mean smooths away. |
| Historical actual/OSRM ratio per corridor | A direct encoding of the W2 audit finding as a feature. |
| Segment count per leg; FTL vs Carting flag | Cheap, likely small gain. |
| is_festival_window (only if the date range covers it) | Navratri–Dussehra 2018 fell in October; Indian road freight congestion during festival weeks is large and India-specific. Verify first; drop if the window is too short. |

All features must remain past-only and time-windowed — the leakage checks from W3 run again on v2. Cache as features_v2; bump the contract version.

### Step 3 — Predict the residual, not the time (Lahari, D2)

Change what the model is asked. Instead of "how long will this leg take?", ask "how wrong will the corridor baseline be?" Train on the difference and add the baseline back at prediction time:

# one new column, one changed label, one addition at the end

df = df.withColumn("residual", col("actual_time") - col("corridor_baseline"))

gbt = GBTRegressor(featuresCol="features", labelCol="residual",

lossType="absolute", maxIter=200, maxDepth=6, stepSize=0.05)

rf  = RandomForestRegressor(featuresCol="features", labelCol="residual", numTrees=300)

pred = model.transform(test).withColumn(

"predicted_time", col("corridor_baseline") + col("prediction"))

Why this cannot lose. A model that learns nothing predicts 0 everywhere and reproduces the baseline exactly — 36.1 minutes. Anything it does learn is pure gain on top. The headline becomes "the corridor baseline reaches 36.1; residual learning corrects it to X", which is both honest and unattackable. Use lossType="absolute" for GBT so the training objective matches the reported metric; RF in MLlib is squared-loss only, so expect GBT to win.

### Step 4 — Evaluate by slice, not just overall (Lahari, D3)

Overall MAE averages away where the model wins. Report MAE and the baseline's MAE side by side for every slice below in w7_model_metrics_v2.csv:

- Corridor support in training: ≥ 30 legs · 10–29 · < 10 · unseen (the baseline has no history for unseen corridors — it must fall back to a global or lane-type mean; report what it actually does)

- FTL vs Carting · distance band (short / medium / long) · departure hour bucket (night / morning / afternoon / evening)

- Overall, for v1 model, v2 model, corridor-mean, corridor-median, LightGBM reference, OSRM

The expected picture: v2 ties the baseline on well-observed corridors and wins on sparse and unseen ones, because a mean over three legs is noise. That is a genuine, reportable finding — learned features generalise where corridor history is thin.

### Step 5 — The adoption decision (D3 weekly sync, logged as D-045)

| Outcome of the sprint | What the team does |
| --- | --- |
| v2 overall MAE < 36.1 (beats the baseline) | Adopt v2. Paper headline for Layer 1 ML: residual correction over a strong statistical baseline. v1 becomes the ablation row ("raw-target RF"). |
| v2 ties overall but wins on sparse/unseen slices with no loss on well-observed | Adopt v2. Headline: matches the baseline where history is rich, generalises where it is thin. Report the slice table as the main ML figure. |
| v2 does not improve on any slice | Keep v1. Reframe honestly (G-09): the ML result is a tie against a strong baseline; switch the Layer 1 deliverable emphasis to the corridor audit, and add a p50/p90 quantile-prediction row in W8 if time allows — for a control tower, an uncertainty band is the more useful product anyway. |

In all three cases both result files stay in benchmarks/raw/, both are cited in the paper, and the stream-equals-batch check from W5 is re-run against whichever PipelineModel is adopted (500/500 must still hold, otherwise the streaming numbers are stale).

# 3. Week 8 — Harden, Publish a URL, Demo, Paper Launch

Gate 8 (final): v1.0 tagged on main · demo rehearsed twice · paper outline + figure set complete with the corridor audit as headline (G-09) · public URL live and linked in the README (G-08) · fresh-clone reproducibility pass green · CFP deadline confirmed and written into docs/decisions.md.

| Member | D1–D2 | D3–D4 | D5 |
| --- | --- | --- | --- |
| Sai Krishna | D1 first hour: look up the CFP deadlines for ICCCNT / ICACCS / ICCCI (and the institutional list) and log the chosen target + deadline as D-046. Everything in Phase 2 keys off this. Demo script authored — quiet dashboard → producer starts → alerts fire on known-bad corridors → order email processed live → Exception Agent notifies through the real channel (G-07) → document agent scores a BOL live → assistant answers a grounded question → India map close. | Rehearsal 1 (he drives); fixes. G-08. Deploy the dashboard to Streamlit Community Cloud reading the cached Parquet + models from a public object store or the repo's release assets (no Spark needed on the host — the dashboard reads caches only). Link in README top. This is the interim URL; Phase 3 moves it to AWS. | Rehearsal 2; final figure export at report quality (every figure from a benchmarks/raw/ file). |
| Lahari | Final metric tables formatted: Layer 1 (v1 + v2 + baselines + slices) and Layer 2 (five agents incl. document extraction clean/noisy). Re-run stream-equals-batch on the adopted model. | G-09. Paper outline with the corridor audit as the headline contribution (273 slower / 512 faster of 1,130, FDR 0.05); D-018 support-threshold instability and threshold sensitivity as the two supporting findings; ML reported per D-045; agent layer framed as a deterministic-core design position with measured verdicts. Section headings with a frozen result assigned to each. Comparison table vs the 5–6 closest published Delhivery-dataset / delay-prediction papers. | Methodology + results section skeletons drafted; every number in the skeleton links to its benchmark file. |
| Mounika | D1. Reproducibility pass: fresh clone → README → boot --check → full run on a machine that has never seen the repo. Every problem found goes into docs/problems.md and is fixed the same day. Archive Parquet caches (v1 and v2), models (v1 and v2), document corpus, TMS DB, and the Kafka-live run as a release asset. | Course-report Part B skeleton per lab manual; data/implementation section skeleton. Cost of the build so far written down (it is ~$0 — say so explicitly; it becomes the baseline for Phase 3's cost table). | v1.0: merge dev → main, tag, GitHub release with the archived assets attached; references file consolidated from everyone's reading notes. |

# 4. Phase 2 — Paper (Weeks 9–10)

Writing begins with results frozen (W7 D3), figures exported (W8), outline done (W8) and citations collected since W1. Target: full draft in two weeks, arXiv preprint posted regardless of venue, then submission to the venue chosen in D-046.

## 4.1 Claims map — what the paper says and what proves it

Every claim below must be traceable to a file. The order is the order of the paper's contribution list.

| # | Claim | Evidence | Owner |
| --- | --- | --- | --- |
| 1 · headline | An FDR-corrected corridor audit localises where a production routing engine is systematically wrong: 273 slower and 512 faster of 1,130 corridors covering 78.6% of legs | w2_corridor_audit.csv, w2_top20_bottlenecks.csv | Lahari |
| 2 | Support-threshold choice changes the answer entirely: the 10-leg and 30-leg top-20 lists share no corridor (D-018) — a methodological warning for corridor-level analysis | w2_corridor_audit_support30.csv | Lahari |
| 3 | Alerting is threshold-insensitive in quality but not in workload: MCC 0.507→0.536 while alert volume falls 98%→49% of legs | w5_threshold_sensitivity.csv | Lahari |
| 4 | A learned residual correction over a strong per-corridor baseline (framed per D-045); OSRM reported as a reference, not as the comparator | w4_model_metrics.csv, w7_model_metrics_v2.csv | Lahari |
| 5 | Streaming serves the batch model with bit-identical predictions at measured throughput, on a live broker | w5_stream_*, w7_kafka_live.json | Mounika |
| 6 | A deterministic-core agent architecture: verdicts computed, prose generated; therefore every agent decision is reproducible and scored | agent_evaluation.md (five agents) | Sai Krishna / Lahari |
| 7 | Document extraction accuracy with a clean-vs-degraded split and a hallucination rate | w7_doc_extraction_eval.json | Sai Krishna / Lahari |
| 8 | The corridor-aggregation code runs unchanged at 50M+ rows with a reported runtime table | scale_appendix.md | Mounika |

## 4.2 What the paper must not claim

- "Beats the production planner" as a headline. OSRM is a route-time planner with no access to corridor history; a model that has seen the corridor's past beating it is not a fair fight. Report OSRM as context, lead with the audit.

- "Multi-agent AI" without the qualifier. The README already says the agents are less agentic than the word suggests. The paper says the same and turns it into a design position (claim 6).

- "Big data" on 145K rows without the scale appendix. Claim 8 is the licence for the phrase; without it, say "distributed".

- The invoice auditor as a pricing result. D-043 already notes the rate band is the corpus's own model. Report it as a document-audit result only.

## 4.3 Ownership

| Member | Paper ownership |
| --- | --- |
| Sai Krishna | Introduction; system architecture; the agentic-AI survey thread; all figures; arXiv upload; submission mechanics |
| Lahari | Methodology; results (Layer 1 + agent evaluation); the delay-prediction survey thread; comparison table; the D-018 and threshold-sensitivity discussion |
| Mounika | Data and implementation; the systems/streaming survey thread; scale appendix; gaps section; references hygiene |

# 5. Phase 3 — One-Week Cloud Deployment on a $40 Credit (Week 11)

The purpose is not to rebuild the system as serverless. It is to add the two cloud pieces that upgrade existing results, plus the one that makes the assistant stronger — and to do it for well under $40. Everything else that could be done on AWS is listed as a backlog at the end, to be picked up only if time and credit remain.

## 5.1 Rules for the week

- Spend cap $40, alarms at $5 / $15 / $30. AWS Budgets on D1 morning to all three emails before any other resource is created. If the $15 alert fires before D4, stop and review in the sync.

- Local path stays intact. boot runs with no AWS configured; cloud backends are selected in .env (STORAGE_BACKEND=s3, OCR_ENGINE=textract, SQL_BACKEND=athena, LLM_PROVIDER=bedrock).

- Never create: any EC2 instance, RDS, MSK, NAT Gateway, OpenSearch, SageMaker, EMR, MWAA, Redshift, Fargate services. Every one of these can spend $40 in days. The public URL stays on Streamlit Community Cloud ($0) — it was already set up in W8.

- Textract runs on a stratified subsample, cached by hash. 150 documents (50 per type, half clean / half noisy) is enough for a valid two-engine comparison and costs a fraction of the full corpus. Every Textract response is written to S3 keyed by the file's SHA-256 before anything else happens, so re-runs are free.

- Region: us-east-1. Broadest service and Bedrock model availability; no cross-region surprises.

- D5 is teardown. Everything except the S3 bucket and the Glue tables (both ≈ $0) is deleted, and the real bill is written into the README.

## 5.2 What is added

| Addition | What it upgrades in the existing repo | AWS services | Est. cost |
| --- | --- | --- | --- |
| Textract as a second OCR engine, benchmarked on a 150-doc subsample | Turns the document-extraction result (G-01) into a two-engine comparison, clean vs degraded, with hallucination rates for both. A result table, not a feature. eval_extraction.py --engine textract produces it with no new evaluation code | Textract, S3 | $4–10 |
| S3 + Glue + Athena over the cached Parquet | A queryable data lake; Athena must reproduce the W2 audit counts (273 / 512 / 1,130) from SQL as a check; and a new read-only `run_sql` MCP tool that makes the RAG assistant materially stronger than vector search alone | S3, Glue Data Catalog, Athena | < $1 |
| Bedrock as a second LLM provider (optional, D4 only if ahead) | Provider portability behind the existing abstraction; the 30-question set re-run for a groundedness comparison | Bedrock, small model | < $2 |

Deferred to a backlog (not in the 11 weeks): EMR Serverless scale run (needs ~$10 and a spare week), SES inbound email → order agent, dashboard on EC2 + CloudFront, Kafka on an AWS broker (already validated live in W7 via Codespaces, so nothing is lost). Each is written up in docs/cloud.md §Backlog with its cost so it can be picked up later without re-planning.

## 5.3 Week 11 — Data lake, OCR benchmark, SQL-backed assistant

Gate C1 (final): budgets set · caches, models and corpus in S3 with checksums · Athena reproduces the W2 audit counts · Textract-vs-Tesseract table exists (clean and degraded) · run_sql MCP tool live and the assistant re-scored · docs/cloud.md complete with the real cost · boot --check green on a machine with no AWS credentials · everything billable torn down. Tag v1.1-cloud.

| Member | D1–D2 | D3–D4 | D5 |
| --- | --- | --- | --- |
| Sai Krishna | Storage abstraction in src/common/: local path vs S3 behind one interface; dashboard and agents read through it; local path unchanged. Athena run_sql MCP tool: read-only, allow-listed tables, row cap 500, byte-scan cap; exposed to the assistant. | Assistant re-run on the 30 questions with SQL available; groundedness delta vs W7 recorded → c1_assistant_sql_compare.json. If ahead: LLM_PROVIDER=bedrock; 30-question set re-run → c1_llm_provider_compare.json. | docs/cloud.md: architecture with the AWS plane, .env matrix, cost table, backlog section. README cloud paragraph + updated diagram. |
| Lahari | Build the stratified 150-doc subsample list (50 per type, half clean / half noisy) and commit it as benchmarks/raw/c1_textract_subsample.json so the comparison is reproducible. OCR_ENGINE=textract wired into the document agent: AnalyzeExpense for invoices, AnalyzeDocument FORMS+SIGNATURES for BOL/POD; every response cached to S3 by SHA-256 before parsing. Dry run on 5 documents; check the bill in Cost Explorer the same afternoon; then the full 150. | eval_extraction.py --engine textract and --engine tesseract on the same 150 → c1_doc_extraction_textract.json, c1_doc_extraction_tesseract_subsample.json. Comparison table: per type, clean vs noisy, weakest-five fields, hallucination rate for both. Writeup: where each engine breaks and why; cost per document from the bill. This is paper appendix material. | Honest scope rewritten: the W7 caveats are closed with file links; the OCR sentence now cites two engines. Sign-off that every README number traces to a file. |
| Mounika | D1 first hour: Budgets at $5/$15/$30, root MFA, three IAM users with MFA, us-east-1 (D-047). Then push clean_v1, features_v1/v2, hub/corridor/audit tables, models, corpus, TMS DB to S3 with a checksum manifest. Glue Data Catalog tables over the Parquet (manual DDL); Athena reproduces the W2 corridor audit counts → c1_athena_audit_recount.json (must match 273 / 512 / 1,130). | Dashboard reads from S3 when STORAGE_BACKEND=s3; Streamlit Cloud deployment switched to S3-backed caches (still $0 hosting). Cost Explorer review D3 and D4; anything unexpected investigated the same day. | Teardown: Textract cache and Parquet kept in S3 (≈ $0/month); nothing else billable left; IAM users' access keys rotated; final Cost Explorer export → README cost table. Merge dev → main, tag v1.1-cloud, release with assets. |

## 5.4 Budget against the $40 credit

| Item | This week | Ongoing per month |
| --- | --- | --- |
| S3 — caches, corpus, models, Textract cache (< 2 GB; free tier covers 5 GB for 12 months) | $0 | $0 – 0.10 |
| Glue Data Catalog (first 1M objects free) + Athena ($5 per TB scanned; the tables are ~100 MB) | < $1 | < $0.50 |
| Textract — 150 pages, mix of AnalyzeExpense and AnalyzeDocument FORMS+SIGNATURES, cached (free tier gives some AnalyzeDocument/AnalyzeExpense pages per month for the first 3 months, which may cover part of this) | $4 – 10 | $0 (cached) |
| Bedrock — optional, small model, ~60 calls | < $2 | $0 |
| Streamlit Community Cloud hosting | $0 | $0 |
| Total | $5 – 13 | < $1 |
| Headroom left of $40 | $27 – 35 |  |

Weeks 7–10 cost $0: Kafka runs in GitHub Codespaces (free allowance), the public URL is Streamlit Community Cloud, and no AWS resource exists before W11 D1. The entire 11-week plan fits inside the $40 credit roughly three times over, which is the margin a first cloud week should have.

If the Textract free tier applies to a new account, the D2 dry run on 5 documents will show $0 in Cost Explorer; in that case widen the subsample toward the full corpus while staying under the free-tier monthly page allowance, and note the split in the comparison table.

# 6. Equal-Distribution Summary (Weeks 7–11)

|  | Sai Krishna | Lahari | Mounika |
| --- | --- | --- | --- |
| Track | AI agents, automation, dashboard, cloud app surface | ML, statistics, all evaluation, paper results | Data, TMS, streaming, MLOps, cloud platform |
| Gaps owned | G-01 (build), G-06, G-07, G-08 | G-01 (judge), G-02, G-04, G-09 | G-03, G-04 (features), G-05, G-10, G-11 |
| Hard week | W7 (four gaps + RAG) | W7 (ML sprint + eval table) | W7 (features v2 + Kafka live + scale appendix + gates) |
| Flagship demo moment | Order email → TMS → alert on the real channel → assistant answers with SQL evidence, on a public URL | "The baseline gets 36.1; residual learning corrects it to X — and here is where it wins" | Kafka → Spark live at measured throughput; the same audit counts from Spark and from Athena SQL |
| Paper thread | Agentic AI as a deterministic-core design position | Corridor audit + support-threshold instability + threshold sensitivity | Systems, streaming, scale |
| Cloud thread | Storage abstraction, Athena MCP tool, Bedrock (optional) | Textract benchmark on the 150-doc subsample | S3/Glue/Athena, budgets, cost & teardown |

# 7. Decision-Log Entries to Add

Numbers continue from D-043. Renumber if any are already taken.

| ID | Decision |
| --- | --- |
| D-044 | Layer 1 results freeze reopened for W7 D1–D3 only, for the residual-target correction. v1 results archived unchanged; v2 written to a new file; both reported. |
| D-045 | ML adoption decision from the sprint (one of the three outcomes in §2.1 Step 5), with the slice table that justified it. |
| D-046 | Paper venue and CFP deadline; arXiv preprint regardless of venue outcome. |
| D-047 | AWS region us-east-1; account structure; budgets at $5/$15/$30 against a hard $40 cap; the never-create list; Textract on a 150-doc stratified subsample. |
| D-048 | Cloud is an optional backend selected in .env; the local path is the reference implementation and must always run. |
| D-049 | Paper headline is the corridor audit; OSRM is reported as context, not as the comparator; "agentic" is qualified as deterministic-core. |

# 8. Risks From Week 7 Onward

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| The ML sprint finds no improvement and eats more than three days | Medium | Hard stop at D3 sync. Outcome 3 in §2.1 Step 5 is a complete, honest plan — the paper does not depend on the ML number. |
| Doc-extraction accuracy comes back low (e.g. < 80% on noisy) | Medium | That is a result, not a failure. Report the clean/noisy split; the Textract comparison in W11 becomes more interesting, not less. Do not tune to the test set. |
| Kafka fights the Codespaces environment | Low–Medium | 3-day rule already in v2.0: if the broker is not up by end of D3, record the attempt in problems.md, try a second machine with Docker (a lab PC or a teammate's laptop), and keep the file-streaming numbers as the fallback with the caveat left in place. |
| CFP deadline is earlier than W10 | Medium | Checked on W8 D1 (D-046). If tight, submit the outline + figures as an extended abstract where the venue allows, and target the next cycle with the full paper; arXiv goes up on schedule either way. |
| Cloud phase breaks the local path | Low | D-048; boot --check on a credential-less machine is part of every cloud gate. |
| Credit overrun | Low | Hard cap $40, alarms at $5/$15/$30 on W11 D1; no instance-based service of any kind; Textract on a subsample, cached by hash, with a 5-doc dry run and a same-day bill check before the full run. |
| Team bandwidth after the course ends | Medium | The cloud phase is already one week and sequenced by value. If it slips, the Textract comparison (Lahari, D1–D3) is the piece to keep; Athena and the MCP tool are the first to drop. |

# 9. Resume Lines After v1.1-cloud (fill in the real numbers)

- Sai Krishna — Built and deployed a multi-agent logistics control tower (LangGraph, MCP, RAG over Athena + vector search, OCR with Tesseract and Textract) with five evaluated agents, a SQL-grounded assistant over an S3/Athena data lake, and a public dashboard; document-extraction F1 0.NN with N% hallucination rate on a labelled corpus.

- Lahari — Designed the evaluation of a delay-prediction and agent system on 145K real shipment records: an FDR-corrected corridor audit of a production routing engine (273 systematically slow corridors), a residual-learning model over a per-corridor baseline (X min MAE), and a two-engine OCR benchmark; owned the results section of a submitted paper.

- Mounika — Engineered the PySpark + Kafka data platform, mock TMS and MLOps loop behind an agentic control tower; validated Kafka → Spark Structured Streaming live at N events/sec; built the S3/Glue/Athena data lake that reproduces the corridor audit from SQL, and kept the entire cloud phase under $Z of a $40 credit.

Every gate from Week 7 onward guarantees a demoable, documented result. Scope cuts, if ever needed, come from the newest cloud addition, never from the core — and never from closing a gap that is already on the register.